## Sheet1
Week Nr. | Date | Project Plan
W1 | 19/09/2022 25/09/2022 | CB + CP Data pre-processing, looking at imputing Customer ID, descriptions and invoices
W2 | 26/09/2022 02/10/2022 | CB: preprocessing of cancelled orders, CP: start of NLP, aggregated dataset
W3 | 03/10/2022 09/10/2022 | CB: preprocessing of partial cancelled orders, CP: basic RFM model, defining twin customers
W4 | 10/10/2022 16/10/2022 | CB: time series CP: finish NLP, tune base model with bayesian opt, created other models, start graph feature engineering.
W5 | 17/10/2022 23/10/2022 | CB: finish time series, CP: finish graph, both start feature selection.
W6 | 24/10/2022 30/10/2022 | Both: finish feature selection
W7 | 31/10/2022 6/11/2022 | Finish model evaluation, write report
W8 | 2022-11-11 | Presentation